## Guidelines for Schedule Metrics
Change Management Approach
The team will take the following approach when a change is requested.
Priority
0 | Reject | Inform client about rejection of change
1 | Low | Functions can be added to tertiary/good-to-have functions
2 | Medium | Discuss with client to rescope the project by reducing current functionalities to cater to the change
3 | High | To be included in project schedule immediately. PM to reschedule tasks.

## Change Log
|  | Mich | Mich |  |  | Mich | Mich
Iteration | Requested On | Change Description | Reason of Change | Change Feasibility | Priority Level | Acknowledgement By | Date of Acknowledgement | Accepted/Rejected | Status
4 | 2014-11-12 | New tab "Documentations" to store relevant administration documents | These are essential documents to be accessible by nursing students in their administration of care. Documents is similar to the investigation tab. | •Include additional tab in Patient Management Page • Adjustments in database to store the documents | 3 | Michelle |  | Accepted | Completed
6 | 2015-01-08 | Documents do not need 30 seconds delay like the investigation tab. Display documents upon logging in. | These documents do not need to be sent to the lab for investigation hence do not need the 30 seconds delay. | •Remove columns that are irrelevant •Remove the 30 seconds delay | 3 | Michelle |  | Accepted | Completed
6 | 2015-01-08 | New input range for vital signs | New input range for vital signs as per client's request | •Include new validations for the vital signs | 3 |  |  | Accepted | Completed
7 | 2015-01-15 | Include intake and output history | Student needs to view the history of intake and output and monitor it as part of the coursework. | •Include new link to a reveal modal that shows the intake and output history respectively | 3 |  |  | Accepted | Completed
8 | 2015-01-15 | Reset case by lecturer. After resetting the case, the Lecturer should still be able to export student's work. | Lecturer needs to review student's work even after the case has been reset to it's initial values as some of the classes are graded. | • Include additional button "reset" in the lecturer's portal • Include new vital_history table in the database to store the history of student's inputs. | 3 |  |  | Accepted | Completed
7 | 2015-01-21 | All clinical charts should be combined except for temperature chart. Temperature chart should be above as a separate chart. | This is a change based on the UT results. Students commented that in the real clinical industry, the charts are combined. Client agreed and requested the change. | • Include additional button to show "All Charts" with the combined charts. | 3 |  |  | Accepted | Completed
8 | 2015-01-28 | Medication table should be dynamically displayed according to the states activated before. | Student should be able to view all previous medications that the patient has been ordered for, by the doctor. | Loop through state_history table to check what states have been activated, show those medications | 3 |  |  | Accepted | Completed
8 | 2015-01-28 | Medication should not be shown if medicine has been discontinued. | Student should know what medication has been discontinued and should not allow them to administer. Previous cases did not have this and hence was not brought up by the client. | • Include new column in medication_prescription and prescription table to determine the medicine should be discontinued in which state | 3 |  |  | Accepted | Completed
|  | iOS mobile application changed to responsive web application | A responsive web application will be able to cater to more devices. | • Use foundation zurb to make the web pages to be responsive. Certain functions should not be available in the responsive web application. | 3 |  |  | Accepted | Completed
|  | PDF recognition case setup | The PDF recognition will ease the case setup as case setup is a cumbersome process. | [5 empty] | Completed
10 | 2015-03-25 | Medication in viewPatientInformation should have date time | Date and time is critical for nurses to know when and what time they should administer the medicine | • Include additional column to display date and time | 3 |  |  | Accepted | Completed
12 | 2015-03-25 | Validate that systolic BP is more than diastolic | Systolic is always higher than diastolic | • Include if else checks to validate | 3 |  |  | Accepted | Completed
12 | 2015-03-25 | Input & Output charts to indicate that it is "ml" and Input change to Intake | The word Input displayed is wrong | • Minor display codes changed | 3 |  |  | Accepted | Completed
12 | 2015-03-25 | Medication history to cahnge to medicine name instaed of barcode | It is hard to tell which medicine from the barcode | • Minor display codes changed | 3 |  |  | Accepted | Completed
12 | 2015-03-25 | Doctor's order to be optional for creation of medicine | Not every case has doctor's order, hence it is optional field not mandatory | • Edited the jsp page and removed the required | 3 |  |  | Accepted | Completed