## Bug Metrics
Iteration 1 (22 September 2014 - 5 October 2014)
Bug Metrics Score |  |  |  | Action
Iteration 1 (22 September 2014 - 5 October 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved

## Guidelines for Bug Metrics
Severity | Point(s) | Description
Low Impact | 1 | User interface display errors, such as out of alignment, colour used is not according to theme. It does not affect the functionality of the system.
High Impact | 5 | The system is functional with some non-critical functionalities are not working.
Critical Impact | 10 | The system is not functional. Bugs have to be fixed before proceeding.
Score Revised | Points in Iteration | Action
0 | Points <= 5 | The system does not need immediate fixing, could be fixed during buffer time or during coding sessions
5 | Points < 10 | Use the planned debugging time in the iteration
10 | Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.