## Iteration 1
Iteration 1 (22 September 2014 - 5 October 2014)
Bug Metrics Score |  | 14 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 1 (22 September 2014 - 5 October 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Login/ Logout (Student) | viewNurseHomePage.jsp | User is still able to access the application after logging out | 2014-10-01 | 5 | High | Solved | Included a protect.jsp in viewNurseHomePage.jsp to prevent user from viewing page after log out | Wei Yi | 04/10/2014
2 | Create Student | viewNurseAccounts.jsp | No success message shown when account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewNurseAccounts.jsp | Wei Yi | 04/10/2014
3 | Create Lecturer | viewLecturerAccounts.jsp | No success message shown when account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewLecturerAccounts.jsp | Wei Yi | 04/10/2014
4 | Create Admin | viewAdminAccounts.jsp | No success message shown when account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewAdminAccounts.jsp | Wei Yi | 04/10/2014
5 | Edit Student Account | viewNurseAccounts.jsp | No success message when student account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewNurseAccounts.jsp | Wei Yi | 04/10/2014
6 | Edit Lecturer Account | viewLecturerAccounts.jsp | No success message when lecturer account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewLecturerAccounts.jsp | Wei Yi | 04/10/2014
7 | Edit Admin Account | viewAdminAccounts.jsp | No success message when admin account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewAdminAccounts.jsp | Wei Yi | 04/10/2014
8 | Delete Student Account | viewNurseAccounts.jsp | No success message when student account is deleted succssfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewNurseAccounts.jsp | Wei Yi | 04/10/2014
9 | Delete Lecturer Account | viewLecturerAccounts.jsp | No success message when Lecturer account is deleted succssfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewLecturerAccounts.jsp | Wei Yi | 04/10/2014
10 | Delete Admin Account | viewAdminAccounts.jsp | No success message when admin account is deleted succssfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewAdminAccounts.jsp | Wei Yi | 04/10/2014

## Iteration 2
Iteration 2 (22 September 2014 - 5 October 2014)
Bug Metrics Score |  | 11 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 2 (22 September 2014 - 5 October 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Edit Practical group account | editPracticalGroupAccount.jsp | User is able to key in lecturer ID which does not exist and success message Is shown | 2014-10-17 | 5 | High Impact | Solved | Changed the textbox in editPracticalGroupAccount to dropdown to eliminate error of typing the lecturer ID that does not exist | Shi Qi | 2014-10-19
2 | Edit Case Scenario (Admin) | editScenario.jsp | User is prompted an a message saying “Activating this case would deactivate other cases” | 2014-10-18 | 5 | High Impact | Solved | Use a text message on the page instead of a pop up to warn user about activating one case will deactivate the other case. | Wei Yi | 2014-10-19
3 | Delete Case Scenario (Admin) | viewScenarioAdmin.jsp | No success message when case is deleted | 2014-10-18 | 1 | Low Impact | Solved | Displayed success message. Previously, the success message was set, but was not displayed on viewScenarioAdmin | Shi Qi | 2014-10-19

## Iteration 3
Iteration 3 (20 October 2014 - 2 November 2014)
Bug Metrics Score |  | 15 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 3 (20 October 2014 - 2 November 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | View Patient's multidisciplinary notes | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | User is able to submit multidisciplinary notes with empty fields | 2014-10-27 | 5 | High Impact | Solved | Added if else statement to check group names and/or condition if multidisciplinary notes is empty, and set error message accordingly | Hui Ping (Grace) | 2014-10-30
2 | View Patient's multidisciplinary notes | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Saved multidisciplinary notes is blank after doing other tasks (update vital signs) | 2014-10-27 | 5 | High Impact | Solved | Debugged it by changing request to sesion and invalid the session only when the student submits not saved | Hui Ping (Grace) | 2014-10-28
3 | View Patient's investigation reports | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Last updated time for despatching report is incorrect | 2014-11-02 | 5 | High Impact | Solved | Set timezone in pages where datetime is formatted. | Wei Yi | 2014-11-02

## Iteration 4
Iteration 4 (3 November 2014 - 15 November 2014)
Bug Metrics Score |  | 5 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 4 (3 November 2014 - 15 November 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Edit Practical Group Account | http://hsemr-wpinapp.rhcloud.com/hsemr/editPracticalGroupAccount.jsp | when user only wants to modify lecturer, they are not required to fill up password. However, database is updated with empty password if password field is left empty. | 2014-11-14 | 5 | High Impact | Solved | Added new method to only update lecturer ID if user only wants to update lecturer-in-charge. | Wei Yi | 2014-11-16

## Iteration 5
Iteration 5 (15 December 2014 - 28 December 2014)
Bug Metrics Score |  | 30 |  | Action | The system does not need immediate fixing, could be fixed during buffer time or during coding sessions
Iteration 4 (3 November 2014 - 15 November 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1899-12-31 | State transition | editStateLecturer.jsp | Null pointer found when no scenario is activated | 2014-12-25 | 5 | High Impact | Unsolved | Added if else statement to catch the null pointer to show a error message | Shi Qi | 2014-12-28
1900-01-01 | Temperature Charts | viewPatientInformation.jsp | Date and time stated is wrong | 2014-12-28 | 5 | High Impact | Unsolved | Printed the dates of vital signs as String on chart instead of Date to avoid conversion error at different platforms | Wei Yi | 2014-12-29
1900-01-02 | Respiratory Rate Chart | viewPatientInformation.jsp | Date and time stated is wrong | 2014-12-28 | 5 | High Impact | Unsolved | Printed the dates of vital signs as String on chart instead of Date to avoid conversion error at different platforms | Wei Yi | 2014-12-29
1900-01-03 | Heart Rate Chart | viewPatientInformation.jsp | Date and time stated is wrong | 2014-12-28 | 5 | High Impact | Unsolved | Printed the dates of vital signs as String on chart instead of Date to avoid conversion error at different platforms | Wei Yi | 2014-12-29
1900-01-04 | Blood Pressure Chart | viewPatientInformation.jsp | Date and time stated is wrong | 2014-12-28 | 5 | High Impact | Unsolved | Printed the dates of vital signs as String on chart instead of Date to avoid conversion error at different platforms | Wei Yi | 2014-12-29
1900-01-05 | SPO Chart | viewPatientInformation.jsp | Date and time stated is wrong | 2014-12-28 | 5 | High Impact | Unsolved | Printed the dates of vital signs as String on chart instead of Date to avoid conversion error at different platforms | Wei Yi | 2014-12-29

## Iteration 6
Iteration 6 (5 Janurary 2015- 11 Janurary 2015)
Bug Metrics Score |  | 20 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 6 (5 Janurary 2015- 11 Janurary 2015)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Create Scenario | http://hsemr-wpinapp.rhcloud.com/hsemr/createScenario.jsp | Scenario created when scenario name is empty | 2015-01-09 | 5 | High Impact | Solved | Added required in the input text for scenario | Shi Qi | 2015-01-10
2 | View Ward Information | http://hsemr-wpinapp.rhcloud.com/hsemr/viewWard1.jsp http://hsemr-wpinapp.rhcloud.com/hsemr/viewWard2.jsp http://hsemr-wpinapp.rhcloud.com/hsemr/viewWard3.jsp http://hsemr-wpinapp.rhcloud.com/hsemr/viewWard4.jsp | Beds displayed are different from the scenarios | 2015-01-09 | 5 | High Impact | Solved | Added a new method in ScenarioDAO to sort the beds in ASC order | Gladys | 2015-01-10
3 | SPO Charts | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Data does not match the time | 2015-01-09 | 5 | High Impact | Solved | Change sql statement in VitalDAO from desc to asc | Grace | 2015-01-10
4 | Blood Pressure Charts | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Data does not match the time | 42013 | 5 | High Impact | Solved | Change sql statement in VitalDAO from desc to asc | Grace | 2015-01-10

## Iteration 7
Iteration 7 (12 Janurary 2015- 24 Janurary 2015)
Bug Metrics Score |  | 15 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 7 (12 Janurary 2015- 24Janurary 2015)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Reset case | http://localhost:8084/hsemr/viewPatientInformation.jsp | Vital signs are not deleted after clicking reset | 2015-01-20 | 5 | High Impact | Solved | Changed the sql statement in VitalDAO | Wei Yi | 2015-01-24
2 | Reset case | http://localhost:8084/hsemr/viewPatientInformation.jsp | Medical history not deleted after clicking reset | 2015-01-20 | 5 | High Impact | Solved | Added new method in MedicationHistoryDAO and edited ProcessResetScenario | Shi Qi | 2015-01-23
3 | View Activated Case Scenario | http://localhost:8084/hsemr/viewWardInformation.jsp | Error message should be displayed when no case is activated | 2015-01-20 | 1 | Low Impact | Solved | Checked for null scenario and added error message | Shi Qi | 2015-01-23
4 | Case Setup - State V2 | http://localhost:8084/hsemr/createScenario.jsp | No error message for case name | 2015-01-20 | 1 | Low Impact | Solved | Added required for case name | Shi Qi | 2015-01-22
5 | Case Setup - State V2 | http://localhost:8084/hsemr/createScenario.jsp | No error message for gender selection | 2015-01-20 | 1 | Low Impact | Solved | Set default gender as Male to avoid this error | Wei Yi | 2015-01-24
7 | Case setup | http://hsemr-wpinapp.rhcloud.com/hsemr/createMedicationBC.jsp | Unable to click frequency drop down list | 2015-01-21 | 1 | Low Impact | Solved | Editted the sql query in frequencyDAO | Shi Qi | 2015-01-23
8 | Case setup | http://hsemr-wpinapp.rhcloud.com/hsemr/createMedicationBC.jsp | Unable to click Route drop down list | 2015-01-21 | 1 | Low Impact | Solved | Editted the sql query in routeDAO | Shi Qi | 2015-01-23

## Iteration 8
Iteration 8 (26 January 2015 - 8 February 2015)
Bug Metrics Score |  | 32 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 6 (5 Janurary 2015- 11 Janurary 2015)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Case Setup - Create Case | http://hsemr-wpinapp.rhcloud.com/hsemr/createScenario.jsp | Unable to create case scenario if the case name contains digits | 2015-02-07 | 5 | High Impact | Solved | Corrected validation and allowed numbers | Shi Qi | 2015-02-08
2 | View Student's Submission | https://hsemr-wpinapp.rhcloud.com/hsemr/viewSubmissionLecturer.jsp | View submission is only based on activated scenario. | 2015-02-07 | 5 | High Impact | Solved | Added two dropdown (Scenario Name and practical group) , for lecturer to view . | Shi Qi | 2015-02-08
3 | Case Setup - Report | https://hsemr-wpinapp.rhcloud.com/hsemr/editReportDocument.jsp | Report cannot be uploaded because path is changed Document cannot be uploaded because path is changed Unable to view report and document | 2015-02-07 | 5 | High Impact | Solved | Path changed to openshift's path in ProcessReportUpload | Shi Qi | 2015-02-08
5 | Case Management - ResetDefault | https://hsemr-wpinapp.rhcloud.com/hsemr/viewSubmissionLecturer.jsp | UI Bug when user clicks on "Reset All" button in admin page | 2015-02-07 | 1 | Low Impact | Solved | Format text to center | Wei Yi | 2015-02-08
6 | Case Management - ResetDefault | https://hsemr-wpinapp.rhcloud.com/hsemr/viewScenarioAdmin.jsp | Report table is deleted instead of resetting the status | 2015-02-07 | 5 | High Impact | Solved | Modify SQL statement from Delete to Update | Wei Yi | 2015-02-08
7 | Case Management - ResetEachCase | https://hsemr-wpinapp.rhcloud.com/hsemr/resetCaseLecturer.jsp | All notes for the case is deleted when it is not supposed to be deleted | 2015-02-07 | 5 | High Impact | Solved | Remove reset statement | Wei Yi | 2015-02-08
11 | Edit Scenario - Report & Document | https://hsemr-wpinapp.rhcloud.com/hsemr/editReportDocument.jsp | no page found. User should be directed back to admin home page | 2015-02-07 | 5 | High Impact | Solved | Redirected to Admin Homepage | Shi Qi | 2015-02-08
12 | Mobile Responsive | https://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Header for multidisciplinary notes is wrong | 2015-02-07 | 1 | Low Impact | Solved | Changed "Medication" to Multidisciplinary" | Shi Qi | 2015-02-08

## Iteration 9
Iteration 9 ( 9 Janurary 2015- 21 Janurary 2015)
Bug Metrics Score |  | 8 |  | Action | Use the planned debugging time in the iteration
Iteration 9 ( 9 Janurary 2015- 21 Janurary 2015)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Create Case & Edit Case | http://hsemr-wpinapp.rhcloud.com/hsemr/createMedicationBC.jsp | User must select discontinue state. However, the medicine might not need to be discontinued | 2015-02-15 | 5 | High Impact | Solved | Added "none" as a selection for users to choose if there are no discontinue state for te medicine | Shi Qi | 2015-02-20
2 | Lecturer View Submissions | http://hsemr-wpinapp.rhcloud.com/hsemr/viewSubmissionLecturer.jsp | Multidisciplinary Notes should be aligned to the left | 2015-02-15 | 1 | Low Impact | Solved | Removed center attribute | Jocelyn | 2015-02-20
3 | Admin Scenario Management | http://hsemr-wpinapp.rhcloud.com/hsemr/viewScenarioAdmin.jsp | Topbar in the lecturer's portal is not shown when page is being scrolled down | 2015-02-15 | 1 | Low Impact | Solved | Fixed the topbar | Jocelyn | 2015-02-20
4 | Lecturer Scenario Management | http://hsemr-wpinapp.rhcloud.com/hsemr/viewScenarioLecturer.jsp | Topbar in the lecturer's portal is not shown when page is being scrolled down | 2015-02-15 | 1 | Low Impact | Solved | Fixed the topbar | Jocelyn | 2015-02-20

## Iteration 10
Iteration 10 ( 23 February 2015- 08 March 2015)
Bug Metrics Score |  | 9 |  | Action | Use the planned debugging time in the iteration
Iteration 9 ( 9 Janurary 2015- 21 Janurary 2015)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Edit Scenario | https://hsemr-wpinapp.rhcloud.com/hsemr/editScenario.jsp | case name, desciption and admission information- when one has error, it shows that all 3 has error | 2015-03-08 | 5 | High Impact | Solved | Separate case name, description, admission information into separate <div> | Gladys | 2015-03-08
2 | Edit Medicine | https://hsemr-wpinapp.rhcloud.com/hsemr/createMedicationBC.jsp | inconsistent layout when there is no medicine created during edit ( reveal modal) and when medicine is already created during the create case stage. | 2015-03-08 | 1 | Low Impact | Solved | Fixed the UI bug by making the layout consistent | Jocelyn | 2015-03-08
3 | mobile version | https://hsemr-wpinapp.rhcloud.com/hsemr/viewScenarioAdmin.jsp | delete button not disabled in grey | 2015-03-08 | 1 | Low Impact | Solved | Displayed a message to allow users to know that user cannot delete when a case is activated | Jocelyn | 2015-03-08
4 | View Lecturer scenario | https://hsemr-wpinapp.rhcloud.com/hsemr/viewScenarioLecturer.jsp | modify the button so it fits if case more than 10 | 2015-03-08 | 1 | Low Impact | Solved | Adjust the width for the buttons | Jocelyn | 2015-03-08
5 | viewScenarioAdmin.jsp | https://hsemr-wpinapp.rhcloud.com/hsemr/viewScenarioLecturer.jsp | See Healthcare Provider's Order does not expand that cell. it expands the cell on the left. | 2015-03-08 | 1 | Low Impact | Solved | Change the div class so that the button expands the information | Jocelyn | 2015-03-08

## Guidelines for Bug Metrics
Point(s) | Severity | Description
1 | Low Impact | User interface display errors, such as out of alignment, colour used is not according to theme. It does not affect the functionality of the system.
5 | High Impact | The system is functional with some non-critical functionalities are not working.
10 | Critical Impact | The system is not functional. Bugs have to be fixed before proceeding.
Score Revised | Points in Iteration | Action
0 | Points <= 5 | The system does not need immediate fixing, could be fixed during buffer time or during coding sessions
5 | Points < 10 | Use the planned debugging time in the iteration
10 | Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Overview
Iteration | Low | High | Critical | Total
1 | 9 | 1 |  | 14
2 | 1 | 2 |  | 11
3 |  | 3 |  | 15
4 |  | 1 |  | 5
5 |  | 6 |  | 30
6 |  | 4 |  | 20
7 | 5 | 2 |  | 15
8 | 2 | 6 |  | 32
9 | 3 | 1 |  | 8
10 | 4 | 1 |  | 9