## Risk Management
Technical Risks
Risk Description | Impact/Consequences | Likelihood | Impact | Category | Mitigation Plan
Team is unfamiliar with technology used (barcode scanning, charting, etc) | Project will be potentially delayed due to incorrect estimates. The quality of the system might not be as satisfactory as there might be more bugs. | High | High | A | Lead developer will research and dicuss with the team. Project Manager to allocate more time to this task.
Servers – Client is unable to provide access to local server during development phase | Application may not be compatible with the client’s server. | High | Low | A | Team to deploy on OpenShift during development phase. Team to know the client's server's specifications and research on deployment prior to deployment to client's server.
Project Management Risks
Risk Description | Impact/Consequences | Likelihood | Impact | Category | Mitigation Plan
Failed to factor in minor coding tasks due to lack of experience. The schedule was planned closely to the BRD and it focuses on the macro functionalities of the whole system | Project will be potentially be delayed because minor coding tasks was not planned for. | Medium | Medium | B | PM has to work closely with the lead developer to bridge the gap between the business functions and the technical components.
Client changes requirements on an ad hoc basis | Project schedule will be affected | Medium | Medium | B | Team to ensure that client requirements are properly documented in a Business Requirements Document before implementation. The BRD serves as a basis for negotiation of any changes. Changes will be reviewed on a case by case basis.
Delay in getting necessary data or information (such as cases used in class, multidisciplinary notes, etc) from the client, hindering the team’s progress of development | Project schedule will be affected | Medium | Medium | B | Team to use mock data to test the system instead. PM to keep steady communication with our client. Also, could call the client as we realised that the client prefers calls, face to face communication rather than emails.
Team Risks
Risk Description | Impact/Consequences | Likelihood | Impact | Category | Mitigation Plan
Team members reluctant to voice out ideas as they want the group to be in harmony and do not want any conflicting views. | The team might potentially miss out good ideas or valid points, affecting the overall quality of the application | Medium | Medium | B | PM should spot and ensure any members who are quiet during the meeting. PM could also go a round table approach whereby everyone has to voice out at least once for a certain idea.

## Guidelines for Risk Management
Likelihood
Impact | Low | Medium | High
High | B | A | A
Medium | C | B | A
Low | C | C | B
|  |  |  | Category | Category | Description
|  |  |  | A | High Risk | Needs the most attention and a developed mitigation strategy
|  |  |  | B | Moderate Risk | Needs lesser attention than high risk
|  |  |  | C | Low Risk | Risk can occur but deserves least amount of planning