## Schedule Metrics Tracking
Iteration | Planned Start Date | Planned End Date | Duration (Days) | Milestone included | Actual Start Date | Actual End Date | Actual Duration (Days) | Schedule Metrics Score | Action | Remarks
Iteration 1 | 2014-09-22 | 2014-10-05 | 14 |  | 2014-09-22 | 2014-10-05 | 14 | 100% | Estimates are generally accurate and on track.
Iteration 2 | 2014-10-06 | 2014-10-19 | 14 |  | 2014-10-06 | 2014-10-19 | 14 | 100% | Estimates are generally accurate and on track.
Iteration 3 | 2014-10-20 | 2014-11-02 | 14 | Proposal | 2014-10-20 | 2014-11-02 | 14 | 100% | Estimates are generally accurate and on track.
Iteration 4 | 2014-11-03 | 2014-11-16 | 14 | Acceptance | 2014-11-03 | 2014-11-15 | 13 | 107.7% | Estimates are generally accurate and on track.
Iteration 5 | 2014-12-15 | 2014-12-28 | 14 |  | 2014-12-15 | 2014-12-29 | 15 | 93.33% | Estimates are generally accurate and on track. | Delayed slightly due to debugging phase, team was unfamiliar with charts. Date/time issue. Date showed NaN.
Iteration 6 | 2014-12-29 | 2015-01-11 | 14 |  | 2014-12-30 | 2015-01-12 | 14 | 100% | Estimates are generally accurate and on track.
Iteration 7 | 2015-01-12 | 2015-01-25 | 14 | UT2, Deployment | 2015-01-13 | 2015-01-26 | 14 | 100% | Estimates are generally accurate and on track.
Iteration 8 | 2015-01-26 | 2015-02-08 | 14 | Beta Release | 2015-01-27 | 2015-02-09 | 14 | 100% | Estimates are generally accurate and on track.
Iteration 9 | 2015-02-09 | 2015-02-22 | 14 | Midterm |  |  | 1
Iteration 10 | 2015-02-23 | 2015-03-08 | 14 |  |  |  | 1
Iteration 11 | 2015-03-09 | 2015-03-22 | 14 |  |  |  | 1
Iteration 12 | 2015-03-23 | 2015-04-05 | 14 |  |  |  | 1
Iteration 13 | 2015-04-06 | 2015-04-19 | 14 |  |  |  | 1
Iteration 14 | 2015-04-20 | 2015-05-03 | 14 | Poster |  |  | 1 | 14
Iteration 15 | 2015-05-04 | 2015-05-17 | 14 | Final |  |  | 1 | 14
Formulas:
Planned End Date = [Planned Start Date]+13
Planned Start Date = [Planned End Date, row above]+1
Actual Start Date = [Actual End Date, row above]+1
Actual End Date = [Actual Start Date]+13
Actual End Date = [Actual Start Date]+13+1

## Overview
Planned Schedule
1
2
3
4
5
6
7
8
9
10
11
Actual Schedule
1
2
3
4
5
6
7

## Guidelines for Schedule Metrics
Score Revised | Score (%) | Action
| SM <= 90 | The team is behind the schedule Under-estimated the effort required Re-estimate tasks for future iterations Deduct the number of days behind schedule from buffer days If there is no more buffer days left, decide to drop any functionalities
| 90 < SM <= 110 | Estimates are generally accurate and on track.
| > 110 | The team is ahead of schedule Over-estimated the effort required Re-estimate tasks for future iterations Add the number of days gained back to the buffer days