## Iteration 1
Iteration 1 (22 September 2014 - 5 October 2014)
Bug Metrics Score |  | 14 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 1 (22 September 2014 - 5 October 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Login/ Logout (Student) | viewNurseHomePage.jsp | User is still able to access the application after logging out | 2014-10-01 | 5 | High | Solved | Included a protect.jsp in viewNurseHomePage.jsp to prevent user from viewing page after log out | Wei Yi | 04/10/2014
2 | Create Student | viewNurseAccounts.jsp | No success message shown when account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewNurseAccounts.jsp | Wei Yi | 04/10/2014
3 | Create Lecturer | viewLecturerAccounts.jsp | No success message shown when account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewLecturerAccounts.jsp | Wei Yi | 04/10/2014
4 | Create Admin | viewAdminAccounts.jsp | No success message shown when account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewAdminAccounts.jsp | Wei Yi | 04/10/2014
5 | Edit Student Account | viewNurseAccounts.jsp | No success message when student account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewNurseAccounts.jsp | Wei Yi | 04/10/2014
6 | Edit Lecturer Account | viewLecturerAccounts.jsp | No success message when lecturer account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewLecturerAccounts.jsp | Wei Yi | 04/10/2014
7 | Edit Admin Account | viewAdminAccounts.jsp | No success message when admin account is created successfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewAdminAccounts.jsp | Wei Yi | 04/10/2014
8 | Delete Student Account | viewNurseAccounts.jsp | No success message when student account is deleted succssfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewNurseAccounts.jsp | Wei Yi | 04/10/2014
9 | Delete Lecturer Account | viewLecturerAccounts.jsp | No success message when Lecturer account is deleted succssfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewLecturerAccounts.jsp | Wei Yi | 04/10/2014
10 | Delete Admin Account | viewAdminAccounts.jsp | No success message when admin account is deleted succssfully | 2014-10-01 | 1 | Low | Solved | Stored success message as an attribute and displayed it on viewAdminAccounts.jsp | Wei Yi | 04/10/2014

## Iteration 2
Iteration 2 (22 September 2014 - 5 October 2014)
Bug Metrics Score |  | 11 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 2 (22 September 2014 - 5 October 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Edit Practical group account | editPracticalGroupAccount.jsp | User is able to key in lecturer ID which does not exist and success message Is shown | 2014-10-17 | 5 | High Impact | Solved | Changed the textbox in editPracticalGroupAccount to dropdown to eliminate error of typing the lecturer ID that does not exist | Shi Qi | 2014-10-19
2 | Edit Case Scenario (Admin) | editScenario.jsp | User is prompted an a message saying “Activating this case would deactivate other cases” | 2014-10-18 | 5 | High Impact | Solved | Use a text message on the page instead of a pop up to warn user about activating one case will deactivate the other case. | Wei Yi | 2014-10-19
3 | Delete Case Scenario (Admin) | viewScenarioAdmin.jsp | No success message when case is deleted | 2014-10-18 | 1 | Low Impact | Solved | Displayed success message. Previously, the success message was set, but was not displayed on viewScenarioAdmin | Shi Qi | 2014-10-19

## Iteration 3
Iteration 3 (20 October 2014 - 2 November 2014)
Bug Metrics Score |  | 15 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 3 (20 October 2014 - 2 November 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | View Patient's multidisciplinary notes | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | User is able to submit multidisciplinary notes with empty fields | 2014-10-27 | 5 | High Impact | Solved | Added if else statement to check group names and/or condition if multidisciplinary notes is empty, and set error message accordingly | Hui Ping (Grace) | 2014-10-30
2 | View Patient's multidisciplinary notes | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Saved multidisciplinary notes is blank after doing other tasks (update vital signs) | 2014-10-27 | 5 | High Impact | Solved | Debugged it by changing request to sesion and invalid the session only when the student submits not saved | Hui Ping (Grace) | 2014-10-28
3 | View Patient's investigation reports | http://hsemr-wpinapp.rhcloud.com/hsemr/viewPatientInformation.jsp | Last updated time for despatching report is incorrect | 2014-11-02 | 5 | High Impact | Solved | Set timezone in pages where datetime is formatted. | Wei Yi | 2014-11-02

## Iteration 4
Iteration 3 (20 October 2014 - 2 November 2014)
Bug Metrics Score |  | 5 |  | Action | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration 3 (20 October 2014 - 2 November 2014)
S/N | Functionality | Files Affected | Description of bug | Date Found | Points | Severity | Status | Action Taken by Developers | Solved by | Date Solved
1 | Edit Practical Group Account | http://hsemr-wpinapp.rhcloud.com/hsemr/editPracticalGroupAccount.jsp | user is able to save even if password field is blank | 2014-11-14 | 5 | High Impact | Unsolved

## Guidelines for Bug Metrics
Point(s) | Severity | Description
1 | Low Impact | User interface display errors, such as out of alignment, colour used is not according to theme. It does not affect the functionality of the system.
5 | High Impact | The system is functional with some non-critical functionalities are not working.
10 | Critical Impact | The system is not functional. Bugs have to be fixed before proceeding.
Score Revised | Points in Iteration | Action
0 | Points <= 5 | The system does not need immediate fixing, could be fixed during buffer time or during coding sessions
5 | Points < 10 | Use the planned debugging time in the iteration
10 | Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.