## Guidelines for Schedule Metrics
Change Management Approach
The team will take the following approach when a change is requested.
Priority
0 | Reject | Inform client about rejection of change
1 | Low | Functions can be added to tertiary/good-to-have functions
2 | Medium | Discuss with client to rescope the project by reducing current functionalities to cater to the change
3 | High | To be included in project schedule immediately. PM to reschedule tasks.

## Change Log
|  | Mich | Mich |  |  | Mich | Mich
Iteration | Requested On | Change Description | Reason of Change | Change Feasibility | Priority Level | Acknowledgement By | Date of Acknowledgement | Accepted/Rejected | Status
4 | 2014-11-12 | New tab "Documentations" to store relevant administration documents | These are essential documents to be accessible by nursing students in their administration of care. Documents is similar to the investigation tab. | •Include additional tab in Patient Management Page • Adjustments in database to store the documents | 3 | Michelle |  | Accepted | Completed
6 | 2015-01-08 | Documents do not need 30 seconds delay like the investigation tab. Display documents upon logging in. | These documents do not need to be sent to the lab for investigation hence do not need the 30 seconds delay. | •Remove columns that are irrelevant •Remove the 30 seconds delay | 3 | Michelle |  | Accepted
6 | 2015-01-08 | New input range for vital signs | New input change for vital signs as previous vital signs seem unrealistic. | •Include new validations for the vital signs | 3 |  |  | Accepted